## AO Tools Development Strategy
No | Task | Role | Suppoter
1 | Acquire and Analysis MQ Message format for Request and Response | Ash/Karl | Kinson
2 | Acquire and analysis Powercurve MQ Architecture diagram | Ash/Karl | Kinson
3 | Analysis and Config the MQ server in Java adodption | Karl/Arvin | Web Resource
4 | Get authorization form ITID(MQ Management team ) | Ash/Karl | ITID
5 | Depoly the system structure into Automation Server | Arvin | Karl
6 | Develop the MQ server connection | Arvin | Karl
7 | Develop the Mapping method for Key-value to MQ Request format | Arvin | Ash/Karl
8 | Develop the Mapping method for Key-value to MQ Response format | Arvin | Ash/Karl
9 | Develop the front-end of MQ Testing page | Kai | Arvin/Ash
10 | Connect the front-end page to back-end by api | Kai | Arvin

## Epic-AO
No | Start Date | End Date | Epic | Key Point | NOTE
Sprint 1 | 2021-03-08 | 2021-03-19 | General Function & API Module | B/E & F/E Framework, Datavbase Build, API Module Pervious work: Back-end API Release, Front-end Page Release | About Requirement chaning that the API Part is already using NTP to testing, Sprint 1 & Spint API Module have been finished and the mean point is to deploy the system into HSBC local environment; therefore, the code structure can be tested.
Sprint 2 | 2021-03-22 | 2021-04-02 | API Module & Code Environment Transformation | Back-end: Finish API Quick Testing Front-end: Finish to connect to BE Back -end code will be deployed into HSBC local envirronment in this sprint, all dependiency will be intalled. | Moreover, base on this sturcture will save efforts form Back-end and Front-end structure building
Sprint 3 | 2021-03-29 | 2021-05-05 | Automation Server Set-up & Powercurve MQ Set-up | In this sprint, BA will finish Powercurve study and find solution to send MQ Request to Powercurve and get Response, and base the MQ Structure to design the front-end function and pages. the code will be set-up in Automation Server, and the API Test will be test in Automation Server Secondary, Back-end will finish the powercurve MQ development that user can send the request to Powercurve and get Response from Powercurve. Front-end will start form page coding and finished at connect to back-end. | Left some time for buffer for MQ developments

## Schedule-AO
Task | March | [23 empty] | April
| 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sprint 1
Sprint 2
Sprint 3
Initial Requirement Kick Of
Requirement
Development
Show Case
SIT
UAT
Final Showcase/Product Delivery