## AO Strategy
No | Task | Role | Suppoter
1 | Acquire and Analysis MQ Message format for Request and Response | Ash/Karl | Kinson
2 | Acquire and analysis Powercurve MQ Architecture diagram | Ash/Karl | Kinson
3 | Acquire and Analysis Powercurve: Message Format/Schema/Catalogue. | Ash/Karl
4 | Analysis Egypt Testing Strategy and Test Case | Ash
5 | Acquire and Analysis SAS: API Format/Number | Ash/Karl
6 | Analysis and Config the MQ server in Java adodption | Karl/Arvin | Web Resource
7 | Get authorization form ITID(MQ Management team ) | Ash/Karl | ITID
8 | Depoly the system structure into Automation Server | Arvin | Karl
9 | Develop the MQ server connection | Arvin | Karl
10 | Develop the Mapping method for Key-value to MQ Request format | Arvin | Ash/Karl
11 | Develop the Mapping method for Key-value to MQ Response format | Arvin | Ash/Karl
12 | Develop the front-end of MQ Testing page | Kai | Arvin/Ash
13 | Connect the front-end page to back-end by api | Kai | Arvin
14 | Matching the API format to MQ format | Ash/Karl | Card Team
15 | Develop the transformation method MQ Response to Json | Arvin | Karl
16 | Develop the compasion method for API Response Json and MQ Response Json | Arvin | Ash/Karl

## Epic-AO
No | Start Date | End Date | Epic | Key Point | NOTE
Sprint 1 | 2021-03-08 | 2021-03-19 | General Function & API Module | B/E & F/E Framework, Datavbase Build, API Module Pervious work: Back-end API Release, Front-end Page Release | About Requirement chaning that the API Part is already using NTP to testing, Sprint 1 & Spint API Module have been finished and the mean point is to deploy the system into HSBC local environment; therefore, the code structure can be tested.
Sprint 2 | 2021-03-22 | 2021-04-02 | API Module & Code Environment Transformation | Back-end: Finish API Quick Testing Front-end: Finish to connect to BE Back -end code will be deployed into HSBC local envirronment in this sprint, all dependiency will be intalled. | Moreover, base on this sturcture will save efforts form Back-end and Front-end structure building
Sprint 3 | 2021-03-29 | 2021-04-23 | Automation Server Set-up & Powercurve MQ Set-up | In this sprint, BA will finish Powercurve study and find solution to send MQ Request to Powercurve and get Response, and base the MQ Structure to design the front-end function and pages. the code will be set-up in Automation Server, and the API Test will be test in Automation Server Secondary, Back-end will finish the powercurve MQ development that user can send the request to Powercurve and get Response from Powercurve. Front-end will start form page coding and finished at connect to back-end.
Sprint4 | 2021-04-12 | 2021-04-30 | Response Transformation & SAS & PowerCurve Response Comparison | When BA get the format of SAS ID API & PowerCurve MQ Message Fromat, the most important part is to match the API to MQ, and we need to transfer the MQ Reponse to Json in order to match with API part. Secondary, when we finished mapping MQ to API, we will develop the Response Comparsion part to test the test case pass or not, then the result will be transacted to NTP to store.

## Schedule-AO
Task | March | [23 empty] | April
| 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Initial Requirement Kick Of
Requirement
Development
Show Case
SIT
UAT
Final Showcase/Product Delivery