## Schedule
FS |  |  | May | June |  |  |  | July |  |  |  | Aug
Sprint # | Items | Stage | Week0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Sprint 1 | API Module | Requirement Clarification
Development
SIT
UAT
Sprint 2 | Admin Module | Requirement Clarification
Development
SIT
UAT
Sprint 3 | SFTP Module | Requirement Clarification
Development
SIT
UAT
Sprint 4 | MQ Module | Requirement Clarification
Development
SIT
UAT
AO |  |  | May | June |  |  |  | July |  |  |  | Aug
Sprint # | Items | Stage | Week0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Sprint 1 | Data Analysis | Requirement Clarification
Development
SIT
UAT
Sprint 2 | API Module | Requirement Clarification
Development
SIT
UAT
Sprint 3 | Test Case Creation | Requirement Clarification
Development
SIT
UAT
Sprint 4 | Test Report | Requirement Clarification
Development
SIT
UAT

## Story (hidden)
[10 empty] | 33356.4 | 28089.6 | 26334 | 31513.02 | 17556
Project Name | NO. | Module Name | Scope | Status | Project Phase | Deliverables | Start date | End date | Estimation HCM | [6 empty] | Estiamtion HC
[9 empty] | Total | PM | BA | BE | FE | Testing | cost by actual effort in this project |  | cost Estimation(CNY) | GP%
FS Global | 1 | Data Analysis | Get all required data sample from support team. | In Progress | Requirement & UI Prototype | 1.Prototype | 2021-06-01 | 2021-06-11 | 4.6 | 0.3 | 0.4 | 2.1 | 1.1 | 0.7 | 123497.682 | 5.5 | 165000 | 23.51%
|  |  | Analyze encrypt request data for AAPS to PCSM. | In Progress | Development | 2.Source Package
|  |  | 1. Develop a tool to decode/encode request data. | In Progress | SIT
|  |  | 2. Develop a tool to distinguish each field for request data. | Not Started
|  |  | 3. Mocking up the data and send to PCSM using SOAP API. | Not Started
|  |  | Analyze request data for AAPS to SAS ID. | Not Started
|  |  | 1. Send request data to SAS ID using Rest API. | Not Started
|  |  | 2. Mapping each field in SAS ID request data to PCSM request data. | Not Started
|  |  | 3. Communication with business team for which field to be changed. | Not Started
|  |  | Analyze each field for response data. | Not Started
|  |  | 1. Get encrypted response data from PCSM after sending request data by SOAP API. | Not Started
|  |  | 2. Decode the request data and convert it to flat messages. | Not Started
|  |  | 3. Get response data from SAS ID after sending request data by Rest API | Not Started
|  |  | Using mapping sheet to make a comparison between PCSM and SAS ID response data | Not Started
| 2 | API Module |  |  | Requirement & UI Prototype | 1.Prototype |  |  | 5.5 | 0.4 | 0.5 | 2.5 | 1.3 | 0.8 | 148234.086 | 6.5 | 195000
[5 empty] | Development | 2.Source Package
SIT
| 3 | Test Case Creation |  |  | Requirement & UI Prototype Confirm | 1.Prototype |  |  | 7.1 | 0.5 | 0.6 | 3.2 | 1.7 | 1.1 | 190684.494 | 8 | 240000
[5 empty] | Development | 2.Source Package
SIT
| 4 | Test Report |  |  | Requirement & UI Prototype Confirm | 1.Prototype |  |  | 1.6 | 0.1 | 0.1 | 0.7 | 0.4 | 0.3 | 42450.408 | 2 | 60000
[5 empty] | Development | 2.Source Package
SIT
| Total Amount(CNY) | [7 empty] | 18.8 | 1.3 | 1.6 | 8.5 | 4.5 | 2.9 | 504866.67 | 22 | 660000

## Resource
Project | Role | Name | Require Skills | 最晚上项目时间 | 成本 | 单价 | 项目天数 | 开始时间 | 结束时间 | Capacity
AO | Tech Leader |  |  | 2021-06-07 | 30096 | 1003.2 | 30 | 2021-06-07 | 2021-08-06 | 0.5
| Java Developer |  |  | 2021-06-07 | 67214.4 | 1003.2 | 67 | 2021-05-31 | 2021-08-06 | 1
| Java Developer |  |  | 2021-06-07 |  |  | 60 | 2021-06-07 | 2021-08-06 | 1
| Junior Java Developer |  |  | 2021-06-07 |  |  | 60 | 2021-06-07 | 2021-08-06 | 1
| React Developer |  |  | 2021-06-07 | 66963.6 | 1116.06 | 60 | 2021-06-07 | 2021-08-06 | 1
| Junior React Developer |  |  | 2021-06-07 |  |  | 60 | 2021-06-07 | 2021-08-06 | 1
| Tester |  | Can be Intern,心细 | 2021-06-14 | 13144 | 496 | 26.5 | 2021-06-14 | 2021-08-06 | 0.5
FS | Tech Leader |  |  | 2021-06-07 | 83265.6 | 1003.2 | 83 | 2021-05-24 | 2021-08-15 | 1
| Java Developer |  |  | 2021-06-07 | 69220.8 | 1003.2 | 69 | 2021-06-07 | 2021-08-15 | 1
| Java Developer |  |  | 2021-06-07 |  |  | 69 | 2021-06-07 | 2021-08-15 | 1
| Junior Java Developer |  |  | 2021-06-07 |  |  | 69 | 2021-06-07 | 2021-08-15 | 1
| React Developer |  |  | 2021-06-07 | 77008.14 | 1116.06 | 69 | 2021-06-07 | 2021-08-15 | 1
| Junior React Developer |  |  | 2021-06-07 | 53934.54 | 781.66 | 69 | 2021-06-07 | 2021-08-15 | 1
| Tester |  | Can be Intern,心细 | 2021-06-14 | 15376 | 496 | 31 | 2021-06-14 | 2021-08-15 | 0.5