## Epic-AM
No | Epic | Key Point
Sprint 1 | General Function & API Module | B/E & F/E Framework, Datavbase Build, API Module Pervious work: Back-end API Release, Front-end Page Release
Sprint 2 | API Module | Back-end: Finish API Quick Testing Front-end: Finish to connect to BE
Sprint 5 | CSV Module | Requirement: Design new User Jounrey for CSV Back-end: Deal with Batch items for HUB Front-end: Pending Item show
Sprint 3 | Test Case | Back-end: Finish to Comparation with expect result Front-end: Compartion display Function
Sprint 4 | Test Report | Back-end: Test Report for Comparation Front-end: Test Report show

## Epic-AO
No | Start Date | End Date | Epic | Key Point
Sprint 1 | 2021-03-08 | 2021-03-19 | General Function & API Module | B/E & F/E Framework, Datavbase Build, API Module Pervious work: Back-end API Release, Front-end Page Release
Sprint 2 | 2021-03-22 | 2021-03-26 | API Module | Back-end: Finish API Quick Testing Front-end: Finish to connect to BE
Sprint 3 | 2021-03-29 | 2021-04-09 | Modify API Module according to specific strategy | Back-end: Finish API full stact testing Front-end: Finish to connect to BE

## Schedule-AM
Task | March | [23 empty] | April | [29 empty] | May
| 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Sprint 1
Sprint 2 | [21 empty] | FE | FE | FE | FE
Sprint 3 | [21 empty] | BE | BE | BE | BE
Sprint 4
Sprint 5
Initial Requirement Kick Of
Requirement
Development
Show Case
SIT
UAT
Final Showcase/Product Delivery

## Schedule-AO
Task | March | [23 empty] | April
| 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Sprint 1
Sprint 2
Sprint 3
Initial Requirement Kick Of
Requirement
Development
Show Case
SIT
UAT
Final Showcase/Product Delivery

## Show Case 1 Question
No. | Question
1 | Mena function design document too high level
2 | HK MCU function design document, is there any specific change and different from Mena site
3 | Does it exist any CSV format or Data Mapping format here?
4 | Data volumn of every CSV? And How many CSV file of one Catch?
5 | How does HCC send bach request to SAS and How to get response.
6 | Reponse is HUB file or CSV file
7 | How to design expectation result? Compare with TRAID or design by Business requirement.